## All features
[7 empty] | Development |  |  | Migration |  |  | Integration |  |  | Licences | Maintenance per year (2nd-5th Year) |  | Support per year (2nd-5th Year) |  | Training |  |  |  | TOTAL for 5 years
Feature | Solution architecture document | Presentation diagram - GARD | Needed for the BC calculation for Lab portal? | Comment | Features | Initial cost | FTE | Working Days | Cost | Systems | Working Days | Cost | Systems | Working Days | Cost | Cost | Percentage of initial cost | Cost | Percentage of initial cost | Cost | For Supporting DevOps - Working Days per Devops | Doc & Demo to Users - Working Days | Cost | HW
Log-in/IAM, Authentication | + | + | + |  | Intergation with existing IAMs/centralized one | 0 | 3 | 10 | 24000 | 2 | 10 | 16000 | 2 | 10 | 16000 | 0 | 10 | 2400 | 15 | 3600 | 3 | 10 | 15200 |  | 95200
Search | + | + | + | Integrate search from Jira and other services (use Open Source tool) | Common search that covers search results mostly from GARD and other Lab test tools/apps | 0 | 2 | 25 | 40000 | 1 | 13 | 10400 | 7 | 15 | 84000 | 0 | 15 | 6000 | 10 | 4000 | 5 | 10 | 16000 |  | 190400
Search GARD | + | + | + | Integrate search from Jira and other services (use Open Source tool) | Common search that covers search results from GARD and other Lab test tools/apps | 0 | 2 | 25 | 40000 | 1 | 13 | 10400 | 3 | 15 | 36000 | 0 | 10 | 4000 | 10 | 4000 | 3 | 10 | 12800 |  | 131200
Dashboard/status | + | + | + | Integration between Jira and Portal Dashboards | Common Dashboards, most of data are fetched from other lab tools + GARD | 0 | 2 | 20 | 32000 | 0 | 0 | 0 | 6 | 15 | 72000 | 0 | 15 | 4800 | 15 | 4800 | 5 | 10 | 16000 |  | 158400
Dashboard/status GARD | + | + | + | Integration between Jira and Portal Dashboards | Common Dashboards, most of data are fetched from GARD | 0 | 2 | 20 | 32000 | 0 | 0 | 0 | 3 | 15 | 36000 | 0 | 10 | 3200 | 15 | 4800 | 2 | 10 | 11200 |  | 111200
Workflow Engine | + | +/- | + | GARD has its own WF engine - investigate if that one can be also used to orchestrate external component (use Open Source tool) | Lab Portal internal Workflow engine tool | 0 | 2 | 15 | 24000 | 0 | 0 | 0 | 2 | 10 | 16000 | 0 | 20 | 4800 | 10 | 2400 | 4 | 0 | 6400 |  | 75200
Portal BE | - | - | + | Custom Lab Portal Microservices: business logic + controllers/adapters | Integration with existing Lab Tools + GARD | 0 | 4 | 30 | 96000 | 0 | 0 | 0 | 7 | 10 | 56000 | 0 | 15 | 14400 | 10 | 9600 | 6 | 0 | 19200 |  | 267200
Portal BE / GARD | - | - | + | Custom Lab Portal Microservices: business logic + controllers/adapters | Most of integration will be done via GARD | 0 | 4 | 25 | 80000 | 0 | 0 | 0 | 4 | 10 | 32000 | 0 | 15 | 12000 | 10 | 8000 | 4 | 0 | 12800 |  | 204800
API Gateway | + | + | + | use Open Source tool | API Gateway - single entry point to the system | 0 | 2 | 15 | 24000 | 0 | 0 | 0 | 4 | 10 | 32000 | 0 | 10 | 2400 | 10 | 2400 | 4 | 0 | 6400 |  | 81600
Notifications | + | + | + | Integration between GARD and Portal Dashboards | Common solution that integrates GARD and notifications from other systems | 0 | 2 | 20 | 32000 | 3 | 10 | 24000 | 3 | 15 | 36000 | 0 | 10 | 3200 | 10 | 3200 | 3 | 10 | 12800 |  | 130400
Service Requests | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Self Services | - | - | + | new/existing | FE for the existing/new Self service system | 0 | 2 | 25 | 40000 | 2 | 10 | 16000 | 2 | 10 | 16000 | 0 | 15 | 6000 | 10 | 4000 | 3 | 10 | 12800 |  | 124800
Change Management | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Problem Management | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Incident Management | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Test automation | + | - | - | Out of the scope |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Capacity management | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Inventory management | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Discovery | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Asset management | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Analytics | + | + | + | use Open Source tools; Needs HW calculation | Data analytics, predictions | 0 | 3 | 60 | 144000 | 0 | 0 | 0 | 1 | 15 | 12000 | 0 | 10 | 14400 | 10 | 14400 | 8 | 15 | 31200 |  | 302400
Analytics Input | + | + | + | use Open Source tools; Needs HW calculation | Logging + auditing | 0 | 3 | 30 | 72000 | 0 | 0 | 0 | 10 | 10 | 80000 | 0 | 10 | 7200 | 10 | 7200 | 4 | 5 | 13600 |  | 223200
Process automation | + | - | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Monitoring | + | + | - | Task for the Monitoring squad |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Reservation Management | + | + | - | Task for the LaaS Squad? |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Content Management System | + | + | + | Used for static pages, notifications, to show content captured from other services.. | CMS system | 0 | 2 | 25 | 40000 | 0 | 0 | 0 | 1 | 5 | 4000 | 0 | 10 | 4000 | 10 | 4000 | 3 | 10 | 12800 |  | 88800
[17 empty] | Total custom development, integrate with partially implemented GARD: | [7 empty] | 1737600
[17 empty] | Total custom development, integrate with fully implemented GARD: | [7 empty] | 1568800
Working hour (EUR):
100
Working hours per day:
8
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GARD, CM, Service ordering, notifications, incident management, inventory, ...
Note on O7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GARD, Monitoring, Test Automation
Note on L14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Migration to new Self Service system