## Cover
LaaS Business Case
Purpose |  | To prepare the business case calcualtion for LaaS
Scope |  | Option B: Open Source tools + Custom Development
Version | Description |  | Shared On | Reviewed By | Remarks
0.1 | First version
Key Assumptions
Category |  | Assumptions
Scope |  | The current focus is on Prio1 labs that includes Bonn & Nuremberg labs
For business case calculations of all options in subsequent slides, all functional requirements have been given equal weight
The requirements are based on the existing user stories. Any addition may impact the overall cost of project development
Hardware Cost |  | Additional HW cost is not required
Software License (Atlassian tools) |  | CAPEX for existing Atlassian applications license and plugins is NIL
CAPEX for new Atlassian plugin Insight, Insight discovery are considered as cost inputs
Project Development Cost (Capex) |  | Change request and feature enhancement cost is assumed as 200,000.00 each year. 10% of this CR cost will be covered by additional plugins from Atlassian.
Miscellaneous |  | For all calculation purpose, 1 Euro = 1.1 USD. Any movement in currency may have an impact on the overall cost
Assuming 6 months warranty post UAT of the feature development
References

## Dashboard
Key Criteria | Values
Functional Coverage | #DIV/0!
Cost (Initial) - Euros | 0.71 M
Cost (Initial + 4 years) - Euros | 2.26 M
Timeline (Initial Solution) | 10
[7 empty] | Initial | Year 1 | Year 2 | Year 3 | Year 4
[6 empty] | Initial | 0.70885 | 0.70885 | 0.70885 | 0.70885 | 0.70885
[6 empty] | Year 1 |  | 0.44713 | 0.44713 | 0.44713 | 0.44713
[6 empty] | Year 2 |  |  | 0.36618 | 0.36618 | 0.36618
[6 empty] | Year 3 |  |  |  | 0.37668 | 0.37668
[6 empty] | Year 4 |  |  |  |  | 0.35736
Cell with green background are editable
Team Size | 7 | members | Timelines | 10 | in months |  | Initial | Year 1 | Year 2 | Year 3 | Year 4
Timelines | 22 | in months | Team Size | 2.99 | members | Capex | 0.70885 | 0.2352 | 0.2352 | 0.2352 | 0.2352
[6 empty] | Opex | 0 | 0.21193 | 0.13098 | 0.14148 | 0.12216
Cost of 7 members for the duration of 10 months:
1 Year Cost | 0.70885 | [5 empty] | Initial (year 1) | Year 2 | Year 3 | Year 4 | Year 5
5 Year Cost | 2.2562 |  |  |  |  | Capex | 0.70885 | 0.94405 | 1.1792 | 1.4144 | 1.6496
[6 empty] | Opex | 0 | 0.21193 | 0.34291 | 0.48439 | 0.60656

## Overall_Cost
Costs | Description | Qty (wherever applicable) | Unit Cost (wherever applicable) | Initial Cost | Year 1 | Year 2 | Year 3 | Year 4 | Total cost | Timelines | 10 | months
HARDWARE (CapEx) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | Cost | 568000
Server(s) | The current HW in DT will support this - No additional cost requried. |  |  | 0 | [5 empty] | Fixed CR Budget | 200000 | each year
Database server(s) | Same as above |  |  | 0
Storage (backup, redundancy, etc) | Same as above |  |  | 0
Any other server component | Same as above |  |  | 0
SOFTWARE (CapEx) |  |  |  | 59091 | 20000 | 20000 | 20000 | 20000
License cost |  |  |  | 0
License costs of any additional tools |  |  |  | 59091 | 20000 | 20000 | 20000 | 20000
PROJECT DEVELOPMENT (CapEx) |  |  |  | 616000 | 204000 | 204000 | 204000 | 204000
Development |  |  |  | 568000 | 0
Travel | Includes travel cost as part of development |  |  | 48000 | 24000 | 24000 | 24000 | 24000
New features & enhancement (CRs) | New features required as per the customer needs |  |  | 0 | 180000 | 180000 | 180000 | 180000
OPERATION & MAINTENANCE (Opex) |  |  |  | 0 | 201838.3333 | 124745 | 134745 | 116345
Hardware Service Maintenance Agreements |  |  |  |  | 0 | 0 | 0 | 0
Software License Maintenance Agreements |  |  |  |  | 29545 | 39545 | 49545 | 59545 |  | 50% of CAPEX cost
Defect detection and removal |  |  |  |  | 132533.3333 | 85200 | 85200 | 56800
Warranty (6 months) |  |  |  |  | 39760
CONTINGENCY & BUFFER |  |  |  | 33754.55 | 21291.9167 | 17437.25 | 17937.25 | 17017.25
Buffer (Capex) |  | 5% |  | 33754.55 | 11200 | 11200 | 11200 | 11200
Buffer (Opex) |  | 5% |  | 0 | 10091.9167 | 6237.25 | 6737.25 | 5817.25
Total Costs |  |  |  | 708845.55 | 447130.25 | 366182.25 | 376682.25 | 357362.25 | 2256202.55
|  |  |  | 0.70885 |  |  |  |  | 2.2562
CAPEX |  |  |  | 708845.55 | 235200 | 235200 | 235200 | 235200
OPEX |  |  |  | 0 | 211930.25 | 130982.25 | 141482.25 | 122162.25

## Software
All prices in Euro |  | Maintenance cost
1 Euro = 1.1 USD | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Reference
Insight - CMDB Asset management | 31818.1818 | 15909 | 15909 | 15909 | 15909 | https://marketplace.atlassian.com/apps/1212137/insight-asset-management?hosting=server&tab=pricing
Insight discovery | 27272.7273 | 13636 | 13636 | 13636 | 13636 | https://marketplace.atlassian.com/apps/1214668/insight-discovery?hosting=server&tab=pricing
Table grid (optional)
Spirent Velocity | [5 empty] | Assuming that we already have Spirent velocity license purchased, so not including any cost here. We will have to get this verified with LaaS squad
Any other plugin
| 59091 | 29545 | 29545 | 29545 | 29545
References
https://gard.telekom.de/gardwiki/pages/viewpage.action?pageId=281947654

## Effort_Development
Effort Distribution (Lifecycle) |  |  |  | Other Effort | Year 1 | Year 2 | Year 3 | Year 4
Design | 12% | 980 |  | Bug Fixing | 20% | 15% | 15% | 10%
Coding & Unit Testing | 60% | 4900 |  | CRs | 25% | 25% | 25% | 25%
Verification (QA) | 15% | 1225
Documentation + Training Material | 5% | 408.3333 |  | Working Hours per month | 160
Environment | 2% | 163 |  | Effective Hours per month | 130 | Effective hours after excluding scrum meeting effort like planning, grooming, review and standup
Acceptance Testing Support | 6% | 490 | person hours | Team Size | 7
| 100% | 8166.3333 |  | Team Capacity per month (in hours) | 910
|  |  |  | Timelines (in months) | 9
|  |  |  | Final Timelines (in months) | 10 | Added 1 more month for initial analysis & UAT
|  |  |  | Warranty | 7%
Activities | Team Size | No. of hours | Effort (in hours) | Remarks
Plugin Development |  |  | 2000
Resource scheduling | 2 | 500 | 1000
IP connectivity | 2 | 500 | 1000
Setup, Configuration and Customization costs |  |  | 2900
Jira | 1 | 400 | 400
Insight | 1 | 400 | 400
Insight discovery | 1 | 400 | 400
Blueprint Orchestration | 1 | 600 | 600
Process Automation | 1 | 800 | 800 | Includes Backup and recovery and Ops task Automation
Additional Integration | 1 | 300 | 300
Analysis |  |  | 980
Testing |  |  | 1225
Training |  |  | 408.3333
Environment Setup |  |  | 163

## Cost_Development
Number of Engineers | 7 |  | Timelines | 10 | Working Hours |  | 160 |  |  | 1.25
Engineer | Cost per hour | Distribution | Cost |  |  |  | EUR | Days
Architect | 100 | 1 | 160000 | Fixed 1 Architect |  | Per Diem | 50 | 7 | 350
Senior Developer / Lead | 60 | 2 | 192000 |  |  | Hotel | 120 | 7 | 840
Developer | 35 | 3 | 168000 |  |  | Taxi | 50 | 7 | 350
QA | 30 | 1 | 48000 | Fixed 1 QA |  | VISA |  |  | 400
|  | 7 | 568000 |  |  | Flight |  |  | 1060
Average Engineer Cost | 50.7143 | [7 empty] | 3000
Travel Cost per week |  |  | 3000
| # Count | Effort (in hours) | Cost
Travel | 16 |  | 48000 | Assuming 2 person travelling for 1 week per month
Travel (subsequent years) | 8 |  | 24000 | Assuming 2 person travelling for 1 quarter per year

## Feature_Coverage
Functionality | Area | Coverage % | Tools | Remarks
Service requests | LaaS
Reservation Management | LaaS
Connection Management | LaaS
Blueprint Orchestration | LaaS
Change management | LaaS
Capacity management | LaaS
Inventory mgmt. • Discovery • License Management | LaaS
Asset Management | LaaS
Process Automation • Backup and recovery • Ops-task automation | LaaS
Average |  | #DIV/0!

## Overall_Cost_BK (hidden)
Costs | Description | Qty (wherever applicable) | Unit Cost (wherever applicable) | Initial Cost (Year 1) | Year 2 | Year3 | Year 4 | Year 5 | Total cost
HARDWARE (CapEx) |  |  |  | 0
Server(s) | The current HW in DT will support this - No additional cost requried. |  |  | 0
Database server(s) | Same as above |  |  | 0
Storage (backup, redundancy, etc) | Same as above |  |  | 0
Any other server component | Same as above |  |  | 0
SOFTWARE (CapEx) |  |  |  | 0
License cost |  |  |  | 0
License costs of any additional tools |  |  |  | 0
PROJECT DEVELOPMENT |  |  |  | 1152300
Analysis | Includes analysis of existing system, user story refinement, system design (high level) |  |  | 156500
Development Cost | Cost related to developing functionalities/plugins and configuration |  |  | 518000
Integration | Integration of modules and tools |  |  | 108000
Functional Testing (QA) | Cost of end to end functional testing |  |  | 187800
Data Migrations (if needed) |  |  |  | 0
Environment setup | Installation & DevOps pipeline setup (CI/CD etc) |  |  | 32000
Travel cost | Includes travel cost as part of development |  |  | 120000
Training | Create manual, training material, actual training etc |  |  | 30000
Configuration and Deployment | System level configuration and deployment
OPERATION & MAINTENANCE (Opex) |  |  |  |  | #REF! | #REF! | #REF! | #REF!
Hardware Service Maintenance Agreements |  |  |  |  | 0 | 0 | 0 | 0
Software License Maintenance Agreements |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Defect detection and removal |  |  |  |  | 230460 | 172845 | 172845 | 115230
New features & enhancement (CRs) | New features required as per the customer needs |  |  |  | 288075 | 288075 | 288075 | 288075
CONTINGENCY & BUFFER
Buffer | Specify (% buffer) | 10% |  | 115230 | #REF! | #REF! | #REF! | #REF!
Total Costs |  |  |  | 1267530 | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
CAPEX |  |  |  | 1152300 | 288075 | 288075 | 288075 | 288075
OPEX | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!

## Project Development Details (hidden)
Effort Distribution (Lifecycle) | [5 empty] | Engineer | Cost per hour
Requirement Analysis | 15% | 1565 |  |  |  | Architect | 100
Design, Coding & Unit Testing | 60% | 6260 |  |  |  | Senior Developer | 50
Verification (QA) - End to End | 18% | 1878 |  |  |  | Junior Developer | 30
Training | 5% | 521.6667 |  |  |  | QA | 30
Environment | 2% | 208.6667
| 100% | 10433.3333 | person days
Travel
[6 empty] | Blended cost per hour | 100
| No. of Services | No. of hours | Effort (in hours) | Team Size | Cost | Remarks
Development |  |  | 5180 |  | 518000
Microservices (data extractor)
Prestudy | 5 | 80 | 400 |  | 40000
Data Analysis | 5 | 80 | 400 |  | 40000
Build Pipeline | 5 | 80 | 400 |  | 40000
Data Storage / Data Warehouse / Metadata | 1 | 280 | 280 |  | 28000
Transformer | 5 | 200 | 1000 |  | 100000
Microservices towards API Gateway | 6 | 400 | 2400 |  | 240000
Connectivity (connectivity from central system to external monitoring tool) | 15 | 20 | 300 |  | 30000
Integration |  |  | 1080 |  | 108000
Integration with each instance of tool | 15 | 40 | 600 |  | 60000
Integration with Portal | 6 | 80 | 480 |  | 48000
Analysis |  |  | 1565 | 1 | 156500
Testing |  |  | 1878 | 1 | 187800
Training | 1 | 300 | 521.6667 |  | 30000 | Documentation on WIKI and other material
Environment Setup |  | 320 | 208.6667 | 1 | 32000
Travel | 12 | 600 | 600 | 2 | 120000