## Cover
Portal Business Case
Purpose |  | To prepare the business case calcualtion for the Portal
Scope |  | Option C (Custom Portal + Open Source)
Version | Description |  | Shared On | Reviewed By | Remarks
1 | First version prepared during Sprint 3 |  | 2019-12-11 | Marin Komadina
1.1 | Incorporated the review comments |  | 2019-12-17 | Vatroslav
1.2 | Taken the fix CR effort of 200,000.00 per year post discussion with Andreas, Vatroslav & Ashima |  | 2019-12-19 | Marin Komadina
1.3 | Cost updated to show initial and 1 year cost separate |  | 2020-01-13
Key Assumptions
Category |  | Assumptions
Scope |  | The current focus is on Prio1 labs that includes Bonn & Nuremberg labs
For business case calculations of all options in subsequent slides, all functional requirements have been given equal weight
The requirements are based on the existing user stories. Any addition may impact the overall cost of project development
Hardware Cost |  | Additional HW cost is not required
Software License |  | No licensed or commercial tool is part of this option
Project Development Cost (Capex) |  | Change request and feature enhancement cost is assumed as 200,000.00 each year.
Miscellaneous |  | For all calculation purpose, 1 Euro = 1.1 USD. Any movement in currency may have an impact on the overall cost
The cost calculation contains mix of senior & junior engineers from Nagarro. The cost may wary if team composition includes mix of Nagarro & DT members.
Assuming 6 months warranty post UAT of the feature development
References
https://gard.telekom.de/gardwiki/display/AUTOLAB/Business+Case+Calculation+-+Portal

## Dashboard
Key Criteria | Values
Functional Coverage | 88.89%
Cost (Initial) - Euros | 1.04 M
Cost (1 year) - Euros | 0.78 M
Cost (5 years) - Euros | 2.48 M
Timeline (Initial Solution) | 16
[7 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
[6 empty] | Year 1 | 0.78183 | 0.78183 | 0.78183 | 0.78183 | 0.78183
[6 empty] | Year 2 |  | 0.61144 | 0.61144 | 0.61144 | 0.61144
[6 empty] | Year 3 |  |  | 0.37834 | 0.37834 | 0.37834
[6 empty] | Year 4 |  |  |  | 0.37834 | 0.37834
[6 empty] | Year 5 |  |  |  |  | 0.33062
Cell with green background are editable
Team Size | 7 | members | Timelines | 16 | in months |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Timelines | 16 | in months | Team Size | 6.86 | members | Capex | 0.78183 | 0.41741 | 0.2352 | 0.2352 | 0.2352
[6 empty] | Opex | 0 | 0.19403 | 0.14314 | 0.14314 | 0.095424
Cost of 7 members for the duration of 16 months:
1 Year Cost | 0.78183 |  |  |  |  | Opex | 0 | 0.19403 | 0.33716 | 0.4803 | 0.57572
5 Year Cost | 2.4806 |  |  |  |  | Capex | 0.78183 | 1.1992 | 1.4344 | 1.6696 | 1.9048

## Overall_Cost
Costs | Description | Qty (wherever applicable) | Unit Cost (wherever applicable) | Initial Cost | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total cost | Timelines | 16 | months
HARDWARE (CapEx) |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | Cost | 908800
Server(s) | The current HW in DT will support this - No additional cost requried. |  |  | 0 | [6 empty] | Fixed CR Budget | 200000 | each year
Database server(s) | Same as above |  |  | 0
Storage (backup, redundancy, etc) | Same as above |  |  | 0
Any other server component | Same as above |  |  | 0
SOFTWARE (CapEx) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
License cost |  |  |  | 0
License costs of any additional tools |  |  |  | 0
PROJECT DEVELOPMENT (CapEx) |  |  |  | 992800 | 744600 | 397533.3333 | 224000 | 224000 | 224000
Development |  |  |  | 908800 | 681600 | 227200
Travel | Includes travel cost as part of development |  |  | 84000 | 63000 | 37000 | 24000 | 24000 | 24000
New features & enhancement (CRs) | New features required as per the customer needs |  |  | 0 |  | 133333.3333 | 200000 | 200000 | 200000
OPERATION & MAINTENANCE (Opex) |  |  |  | 0 | 0 | 184789.3333 | 136320 | 136320 | 90880
Hardware Service Maintenance Agreements | [5 empty] | 0 | 0 | 0 | 0
Software License Maintenance Agreements | [5 empty] | 0 | 0 | 0 | 0
Bug Fixing | [5 empty] | 121173.3333 | 136320 | 136320 | 90880
Warranty (6 months) | [5 empty] | 63616
CONTINGENCY & BUFFER |  |  |  | 49640 | 37230 | 29116.1333 | 18016 | 18016 | 15744
Buffer (Capex) |  | 5% |  | 49640 | 37230 | 19876.6667 | 11200 | 11200 | 11200
Buffer (Opex) |  | 5% |  | 0 | 0 | 9239.4667 | 6816 | 6816 | 4544
Total Costs |  |  |  | 1042440 | 781830 | 611438.8 | 378336 | 378336 | 330624 | 2480564.8
|  |  |  | 1.0424 | 0.78183 |  |  |  |  | 2.4806
CAPEX |  |  |  | 1042440 | 781830 | 417410 | 235200 | 235200 | 235200
OPEX |  |  |  | 0 | 0 | 194028.8 | 143136 | 143136 | 95424

## Effort_Development
Effort Distribution (Lifecycle) | [6 empty] | Other Effort | Year 1 | Year 2 | Year 3 | Year 4
Design | 13% | 1568.3871 |  |  |  |  | Bug Fixing | 20% | 15% | 15% | 10%
Coding & Unit Testing, Envrionment, Integration | 62% | 7480 |  |  |  |  | CRs | 25% | 25% | 25% | 25%
Verification (QA) | 15% | 1809.6774
Documentation + Training Material | 4% | 482.5806 |  |  |  |  | Working Hours per month | 160
Environment |  | 0 |  |  |  |  | Effective Hours per month | 130 | Effective hours after excluding scrum meeting effort like planning, grooming, review and standup
Acceptance Testing Support | 6% | 723.871 | person hours |  |  |  | Team Size | 7
Data Migration |  | 1304 |  |  |  |  | Team Capacity per month (in hours) | 910
| 100% | 13368.5161 |  |  |  |  | Timelines (in months) | 15
[7 empty] | Final Timelines (in months) | 16 | Added 1 more month for initial analysis & UAT
[7 empty] | Warranty | 7%
Activities | Days | Hours | Days | Hours | Days | Hours | Remarks
| 7480 |  |  |  | 1304
Features | Development |  | Integration |  | Migration
Log-in/IAM, Authentication | 28 | 224 | 20 | 160 | 20 | 160
Search | 50 | 400 | 120 | 960 | 13 | 104
Search GARD | 0 | 0 | 0 | 0 | 0 | 0
Dashboard/status | 40 | 320 | 105 | 840 | 0 | 0
Dashboard/status GARD | 0 | 0 | 0 | 0 | 0 | 0
Workflow Engine | 35 | 280 | 20 | 160 | 0 | 0
Portal BE | 120 | 960 | 80 | 640 | 0 | 0
Portal BE / GARD | 0 | 0 | 0 | 0 | 0 | 0
API Gateway | 30 | 240 | 50 | 400 | 0 | 0
Notifications | 45 | 360 | 60 | 480 | 30 | 240
Self Services | 50 | 400 | 30 | 240 | 20 | 160
Problem Management | 40 | 320 | 10 | 80 | 20 | 160
Incident Management | 40 | 320 | 10 | 80 | 20 | 160
Analytics Input | 0 | 0 | 110 | 880 | 0 | 0 | Development cost removed as Monitoring is providing Analytics
Content Management System | 70 | 560 | 30 | 240 | 40 | 320
|  | 4384 |  | 5160 |  | 1304
3096

## Cost_Development
Number of Engineers | 7 |  | Timelines | 16 | Working Hours |  | 160 |  |  | 1.25
Engineer | Cost per hour | Distribution | Cost |  |  |  | EUR | Days
Architect | 100 | 1 | 256000 | Fixed 1 Architect |  | Per Diem | 50 | 7 | 350
Senior Developer | 60 | 2 | 307200 |  |  | Hotel | 120 | 7 | 840
Junior Developer | 35 | 3 | 268800 |  |  | Taxi | 50 | 7 | 350
QA | 30 | 1 | 76800 | Fixed 1 QA |  | VISA |  |  | 400
|  | 7 | 908800 |  |  | Flight |  |  | 1060
Average Engineer Cost | 50.7143 | [7 empty] | 3000
Travel Cost per week |  |  | 3000
| # Count | Effort (in hours) | Cost
Travel | 28 |  | 84000 | Assumed 28 travels in 16 months
Travel (subsequent years) | 8 |  | 24000 | Assuming 2 person travelling for 1 quarter per year

## Estimates_Architect
[7 empty] | Development | [11 empty] | Migration |  |  |  | Integration |  |  |  | Licences | Maintenance per year (2nd-5th Year) |  | Support per year (2nd-5th Year) |  | Training |  |  |  |  | TOTAL for 5 years
Feature | Solution architecture document | Presentation diagram - GARD | Needed for the BC calculation for Lab portal? | Comment | Features | Initial cost | Sys Admin FTE | Sys Admin - Working Days | BE FTE | BE - Working days | FE FTE | FE - Working days | No of FTE at the same time | Duration - Working Days | Actual Duration - Working Days | Total Working Days | Actual working days | Cost | Systems | Working Days | Actual working days | Cost | Systems | Working Days | Actual working days | Cost | Cost | Percentage of initial development cost | Cost | Percentage of initial development cost | Cost | For Supporting DevOps - Working Days per Devops | Devops Cost | Doc & Demo to Users - Working Days | Demo Cost | HW
Log-in/IAM, Authentication | + | + | + |  | Integration with ZAM | 0 | 1 | 8 | 1 | 10 | 1 | 10 | 3 | 10 | 13.3333 | 28 | 37.3333 | 11200 | 2 | 10 | 13.3333 | 8000 | 2 | 10 | 13.3333 | 8000 | 0 | 10 | 1120 | 15 | 1680 | 3 | 3600 | 10 | 4000 |  | 46000 | 27200 | 7600 | 2800
Search | + | + | + | Integrate search from Jira and other services (use Open Source tool) | Common search that covers search results mostly from GARD and other Lab test tools/apps | 0 | 1 | 10 | 1 | 25 | 1 | 15 | 2 | 30 | 40 | 50 | 66.6667 | 20000 | 1 | 13 | 17.3333 | 5200 | 8 | 15 | 20 | 48000 | 0 | 15 | 3000 | 10 | 2000 | 5 | 6000 | 10 | 4000 |  | 103200 | 73200 | 10000 | 5000
Search GARD | + | + | + | Integrate search from Jira and other services (use Open Source tool) | Common search that covers search results from GARD and other Lab test tools/apps | 0 | 2 | [6 empty] | 25 | 33.3333 | 0 | 0 | 0 | 1 | 13 | 17.3333 | 5200 | 3 | 15 | 20 | 18000 | 0 | 10 | 0 | 10 | 0 | 3 | 2400 | 10 | 4000 |  | 29600 |  |  | 0
Dashboard/status | + | + | + | Integration between Jira and Portal Dashboards | Common Dashboards, most of data are fetched from other lab tools + GARD | 0 | 1 | 10 | 1 | 10 | 1 | 20 | 2 | 25 | 33.3333 | 40 | 53.3333 | 16000 | 0 | 0 | 0 | 0 | 7 | 15 | 20 | 42000 | 0 | 15 | 2400 | 15 | 2400 | 5 | 6000 | 10 | 4000 |  | 87200 | 58000 | 10000 | 4800
Dashboard/status GARD | + | + | + | Integration between Jira and Portal Dashboards | Common Dashboards, most of data are fetched from GARD | 0 | 2 | [6 empty] | 20 | 26.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 15 | 20 | 18000 | 0 | 10 | 0 | 15 | 0 | 2 | 1600 | 10 | 4000 |  | 23600 |  |  | 0
Workflow Engine | + | +/- | + | GARD has its own WF engine - investigate if that one can be also used to orchestrate external component (use Open Source tool) | Lab Portal internal Workflow engine tool | 0 | 1 | 10 | 1 | 25 | 0 | 0 | 2 | 25 | 33.3333 | 35 | 46.6667 | 14000 | 0 | 0 | 0 | 0 | 2 | 10 | 13.3333 | 8000 | 0 | 20 | 2800 | 10 | 1400 | 4 | 3200 | 0 | 0 |  | 42000 | 22000 | 3200 | 4200
Portal BE | - | - | + | Custom Lab Portal Microservices: business logic + controllers/adapters | Integration with existing Lab Tools + GARD | 0 | 1 | 15 | 3 | 35 | 0 | 0 | 4 | 35 | 46.6667 | 120 | 160 | 48000 | 0 | 0 | 0 | 0 | 8 | 10 | 13.3333 | 32000 | 0 | 15 | 7200 | 10 | 4800 | 5 | 8000 | 0 | 0 |  | 136000 | 80000 | 8000 | 12000
Portal BE / GARD | - | - | + | Custom Lab Portal Microservices: business logic + controllers/adapters | Most of integration will be done via GARD | 0 | 4 | [6 empty] | 25 | 33.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 13.3333 | 16000 | 0 | 15 | 0 | 10 | 0 | 4 | 6400 | 0 | 0 |  | 22400 |  |  | 0
API Gateway | + | + | + | use Open Source tool | API Gateway - single entry point to the system | 0 | 1 | 15 | 1 | 10 | 1 | 5 | 2 | 15 | 20 | 30 | 40 | 12000 | 0 | 0 | 0 | 0 | 5 | 10 | 13.3333 | 20000 | 0 | 10 | 1200 | 10 | 1200 | 4 | 4800 | 0 | 0 |  | 46400 | 32000 | 4800 | 2400
Notifications | + | + | + | Integration between GARD and Portal Dashboards | Common solution that integrates GARD and notifications from other systems | 0 | 1 | 10 | 1 | 15 | 1 | 20 | 2 | 20 | 26.6667 | 45 | 60 | 18000 | 3 | 10 | 13.3333 | 12000 | 4 | 15 | 20 | 24000 | 0 | 10 | 1800 | 10 | 1800 | 3 | 3600 | 10 | 4000 |  | 76000 | 54000 | 7600 | 3600
Service Requests | + | + | - | Task for the LaaS Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Self Services | - | - | + | new/existing | FE for the existing/new Self service system | 0 | 1 | 10 | 1 | 20 | 1 | 20 | 3 | 25 | 33.3333 | 50 | 66.6667 | 20000 | 2 | 10 | 13.3333 | 8000 | 3 | 10 | 13.3333 | 12000 | 0 | 15 | 3000 | 10 | 2000 | 3 | 3600 | 10 | 4000 |  | 67600 | 40000 | 7600 | 5000
Change Management | + | + | - | Task for the LaaS Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Problem Management | + | + | + | What tool to use? Estimation is on very high level |  |  | 1 | 10 | 1 | 15 | 1 | 15 | 3 | 20 | 26.6667 | 40 | 53.3333 | 16000 | 1 | 20 | 26.6667 | 8000 | 1 | 10 | 13.3333 | 4000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28000 | 28000 | 0 | 0
Incident Management | + | + | + | Bugzilla/MantisBT/Redmine ? - setup, configure, adapt, higlh level estimation |  |  | 1 | 10 | 1 | 15 | 1 | 15 | 3 | 20 | 26.6667 | 40 | 53.3333 | 16000 | 1 | 20 | 26.6667 | 8000 | 1 | 10 | 13.3333 | 4000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28000 | 28000 | 0 | 0
Test automation | + | - | - | Out of the scope for the Program Increment 1 | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Capacity management | + | + | - | Task for the Monitoring Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Inventory management | + | + | - | Task for the LaaS Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Discovery | + | + | - | Task for the LaaS Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Asset management | + | + | - | Task for the LaaS Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Analytics | + | + | - | Task for the Monitoring squad | Data analytics, predictions | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Analytics Input | + | + | + | use Open Source tools; Needs HW calculation | Logging + auditing | 0 | 1 | 25 | 1 | 30 | 1 | 30 | 3 | 35 | 46.6667 | 85 | 113.3333 | 34000 | 0 | 0 | 0 | 0 | 11 | 10 | 13.3333 | 44000 | 0 | 10 | 3400 | 10 | 3400 | 4 | 4800 | 5 | 2000 |  | 112000 | 78000 | 6800 | 6800
Process automation | + | - | - | Task for the LaaS Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Monitoring | + | + | - | Task for the Monitoring squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Reservation Management | + | + | - | Task for the LaaS Squad | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Content Management System | + | + | + | Content Management System is responsible for managing the lab related information - documents | Document Management System | 0 | 1 | 10 | 1 | 30 | 1 | 30 | 3 | 35 | 46.6667 | 70 | 93.3333 | 28000 | 2 | 20 | 26.6667 | 16000 | 2 | 15 | 20 | 12000 | 0 | 10 | 2800 | 10 | 2800 | 5 | 6000 | 10 | 4000 |  | 88400 | 56000 | 10000 | 5600
Analysis cost | [13 empty] | 200 |  |  |  | 80000 | [9 empty] | Total for custom development, integrate with partially implemented GARD: | [8 empty] | 936400 | 576400 | 75600 | 52200
Support (Scrum, Manager) | [13 empty] | 200 |  |  |  | 80000
CRs/Enhancements | Year 2 | Year 3 | Year 4 | Year 5 | [33 empty] | 144100
| 0.25 | 0.25 | 0.25 | 25% | [33 empty] | 576400
Travel cost (8 travels for 1 week each (3000 per travel, including Visa, Airfare, Hotel, Perdiem) | [17 empty] | 24000
Working hour (EUR):
50 | Blended rate of resource/hour
Working hours per day:
8
Actual working hours per days
6
Start Date
2020-01-01
TIMELINE
Feature | Solution architecture document | Presentation diagram - GARD | Needed for the BC calculation for Lab portal? | Start Date | End date | FTE | Actual Working Days - Total | Actual Working Hours - Total
Log-in/IAM, Authentication | + | + | + | 2020-01-01 | 2020-03-24 | 3 | 59 | 354
Search | + | + | + | 2021-05-24 | 2021-10-13 | 2 | 102.3333 | 614
Search GARD | + | + | + |  | 1900-04-30 | 0 | 86.6667 | 520
Dashboard/status | + | + | + | 2021-02-03 | 2021-05-24 | 2 | 78.3333 | 470
Dashboard/status GARD | + | + | + |  | 1900-03-23 | 0 | 60.6667 | 364
Workflow Engine | + | +/- | + | 2020-03-04 | 2020-08-04 | 1 | 109.3333 | 328
Portal BE | - | - | + | 2020-03-04 | 2021-02-03 | 1.3333 | 240 | 480
Portal BE / GARD | - | - | + |  | 1900-03-27 | 0 | 62.6667 | 376
API Gateway | + | + | + | 2020-01-01 | 2020-03-04 | 2 | 45.3333 | 272
Notifications | + | + | + |  |  | 2 | 79 | 474
Service Requests | + | + | - |  |  | 0 | 0 | 0
Self Services | - | - | + | 2020-03-24 | 2020-09-04 | 2 | 118.5 | 474
Change Management | + | + | - |  |  | 0 | 0 | 0
Problem Management | + | + | + | 2020-08-11 | 2020-12-29 | 2 | 100 | 400
Incident Management | + | + | + | 2020-03-24 | 2020-08-11 | 2 | 100 | 400
Test automation | + | - | - |  |  | 0 | 0 | 0
Capacity management | + | + | - |  |  | 0 | 0 | 0
Inventory management | + | + | - |  |  | 0 | 0 | 0
Discovery | + | + | - |  |  | 0 | 0 | 0
Asset management | + | + | - |  |  | 0 | 0 | 0
Analytics | + | + | - |  |  | 0 | 0 | 0
Analytics Input | + | + | + | 2020-09-04 | 2021-02-12 | 2 | 115.5 | 462
Process automation | + | - | - |  |  | 0 | 0 | 0
Monitoring | + | + | - |  |  | 0 | 0 | 0
Reservation Management | + | + | - |  |  | 0 | 0 | 0
Content Management System | + | + | + | 2020-12-29 | 2022-05-10 | 1 | 355 | 710
|  |  |  | Latest date (actually it is sooner as other tasks will finish earlier, on 13.10.2021): | 2022-05-10
Formulas:
Comment = [Features, row below]
Features = WORKDAY([Comment],[Development])
Note on Y6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GARD, ZAM, CM, Service ordering, notifications, incident management, inventory, ...
Note on Y7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GARD, Monitoring, Test Automation
Note on U14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Migration to new Self Service system

## Feature_Coverage
Functionality | Area | Coverage %
Incident management | Portal | 90%
Change management | LaaS | 100%
Problem management | Portal | 90%
Service requests | LaaS | 100%
Inventory mgmt./Asset mgmt. | LaaS | 100%
User management (IAM, login etc.) | Portal | 100%
Dashboards | Portal | 100%
Search Engine | Portal | 100%
Content management | Portal | 80%
Work-flow engine | Portal | 80%
Notification/Alerts | Portal | 80%
Self-services | Portal | 80%
Capacity mgmt./Reservation mgmt. | LaaS | 85%
Monitoring | Monitoring | 0%
Analytics | Monitoring | 100%
Blueprinting | LaaS | 100%
88.89%

## Overall_Cost_BK (hidden)
Costs | Description | Qty (wherever applicable) | Unit Cost (wherever applicable) | Initial Cost (Year 1) | Year 2 | Year3 | Year 4 | Year 5 | Total cost
HARDWARE (CapEx) |  |  |  | 0
Server(s) | The current HW in DT will support this - No additional cost requried. |  |  | 0
Database server(s) | Same as above |  |  | 0
Storage (backup, redundancy, etc) | Same as above |  |  | 0
Any other server component | Same as above |  |  | 0
SOFTWARE (CapEx) |  |  |  | 0
License cost |  |  |  | 0
License costs of any additional tools |  |  |  | 0
PROJECT DEVELOPMENT |  |  |  | 1152300
Analysis | Includes analysis of existing system, user story refinement, system design (high level) |  |  | 156500
Development Cost | Cost related to developing functionalities/plugins and configuration |  |  | 518000
Integration | Integration of modules and tools |  |  | 108000
Functional Testing (QA) | Cost of end to end functional testing |  |  | 187800
Data Migrations (if needed) |  |  |  | 0
Environment setup | Installation & DevOps pipeline setup (CI/CD etc) |  |  | 32000
Travel cost | Includes travel cost as part of development |  |  | 120000
Training | Create manual, training material, actual training etc |  |  | 30000
Configuration and Deployment | System level configuration and deployment
OPERATION & MAINTENANCE (Opex) |  |  |  |  | #REF! | #REF! | #REF! | #REF!
Hardware Service Maintenance Agreements |  |  |  |  | 0 | 0 | 0 | 0
Software License Maintenance Agreements |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Defect detection and removal |  |  |  |  | 230460 | 172845 | 172845 | 115230
New features & enhancement (CRs) | New features required as per the customer needs |  |  |  | 288075 | 288075 | 288075 | 288075
CONTINGENCY & BUFFER
Buffer | Specify (% buffer) | 10% |  | 115230 | #REF! | #REF! | #REF! | #REF!
Total Costs |  |  |  | 1267530 | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
CAPEX |  |  |  | 1152300 | 288075 | 288075 | 288075 | 288075
OPEX | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!

## Project Development Details (hidden)
Effort Distribution (Lifecycle) | [5 empty] | Engineer | Cost per hour
Requirement Analysis | 15% | 1565 |  |  |  | Architect | 100
Design, Coding & Unit Testing | 60% | 6260 |  |  |  | Senior Developer | 50
Verification (QA) - End to End | 18% | 1878 |  |  |  | Junior Developer | 30
Training | 5% | 521.6667 |  |  |  | QA | 30
Environment | 2% | 208.6667
| 100% | 10433.3333 | person days
Travel
[6 empty] | Blended cost per hour | 100
| No. of Services | No. of hours | Effort (in hours) | Team Size | Cost | Remarks
Development |  |  | 5180 |  | 518000
Microservices (data extractor)
Prestudy | 5 | 80 | 400 |  | 40000
Data Analysis | 5 | 80 | 400 |  | 40000
Build Pipeline | 5 | 80 | 400 |  | 40000
Data Storage / Data Warehouse / Metadata | 1 | 280 | 280 |  | 28000
Transformer | 5 | 200 | 1000 |  | 100000
Microservices towards API Gateway | 6 | 400 | 2400 |  | 240000
Connectivity (connectivity from central system to external monitoring tool) | 15 | 20 | 300 |  | 30000
Integration |  |  | 1080 |  | 108000
Integration with each instance of tool | 15 | 40 | 600 |  | 60000
Integration with Portal | 6 | 80 | 480 |  | 48000
Analysis |  |  | 1565 | 1 | 156500
Testing |  |  | 1878 | 1 | 187800
Training | 1 | 300 | 521.6667 |  | 30000 | Documentation on WIKI and other material
Environment Setup |  | 320 | 208.6667 | 1 | 32000
Travel | 12 | 600 | 600 | 2 | 120000